## Tasks
Renova DevAx M2M
Task ID | Task Name | Assignee | Start Date | Due Date | Time Estimate | Difficult
I | Build up schedule | Minh Le | 2021-02-13 | 2021-02-14 | 3h | DONE
| Build up Schedule |  |  |  | 2h
| Initial Git |  |  |  | 30m
| Initial Project |  |  |  | 30h
II | 0. Getting Started | Uyen | 2021-02-17 | 2021-02-17 | 2h | NORMAL
| Setup network follow the Diagram |  |  |  | 1h | NORMAL
| Setup Remote Host |  |  |  | 30m | LOW
| AWS CLI Configuration |  |  |  | 30m | NORMAL
III | 1. Migrating the Monolith | Uyen | 2021-02-17 | 2021-02-18 | 3h 45m | NORMAL
| Verify network design |  |  |  | 15m | LOW
| Creating RDS - MySQL Instance |  |  |  | 30m | NORMAL
| Setting Up RDS |  |  |  | 30m | NORMAL
| Testing Application Locally |  |  |  | 15m | NORMAL
| Deploy Application to Elastic Beanstalk |  |  |  | 1h | NORMAL
| Change & Update Application |  |  |  | 30m | NORMAL
| Working with AWS SDKs |  |  |  | 30m | NORMAL
| Review Chapter Results |  |  |  | 15m | NORMAL
IV | 2. Configuring Application Release Automation | Uyen | 2021-02-19 | 2021-02-20 | 5h | HIGH
| Config Release Automation |  |  |  | 1h | NORMAL
| Setup Automation Deployment |  |  |  | 1h | NORMAL
| Deploy Windows Service using AWS CodeDeploy |  |  |  | 3h | HIGH
| Service Monitoring |  |  |  | 30m | NORMAL
| Challenge - Do changes in App Source |  |  |  | 15m | NORMAL
| Review Chapter Results |  |  |  | 15m | NORMAL
V | 3. Create a Microservice | Uyen | 2021-02-21 | 2021-02-22 | 5h 15m | HIGH
| Create a Serverless Microservice |  |  |  | 1h 30m | HIGH
| Extending Serverless Microservice |  |  |  | 1h 30m | HIGH
| Automate deployment with CodeStar |  |  |  | 1h | HIGH
| Challenge - Expose the Microservice API |  |  |  | 1h | HIGH
| Review Chapter Results |  |  |  | 15m | NORMAL
VI | 4. Refactor Your Data & Workflows | Uyen | 2021-02-23 | 2021-02-25 | 6h | HIGH
| Create a Scan & Query Microservice |  |  |  | 30m | NORMAL
| Automate Microservice |  |  |  | 30m | NORMAL
| Create API for Microservice |  |  |  | 30m | NORMAL
| Challenge - Enhance TripSearch Microservice |  |  |  | 1h | HIGH
| Create Microservice by AWS Step Functions |  |  |  | 1h | HIGH
| Challenge - Enhance Calculator Service |  |  |  | 45m | NORMAL
| Challenge - Implement An Image Manager Workflow |  |  |  | 1h 30m | HIGH
| Review Chapter Results |  |  |  | 15m | NORMAL
VII | 5. Microservices Messaging & Eventing | Minh Le | 2021-02-17 | 2021-02-18 | 4h 15m | HIGH
| Messaging Options |  |  |  | 2h | HIGH
| Implementing Message Streaming using Kinesis |  |  |  | 1h | HIGH
| Challenge |  |  |  | 1h | HIGH
| Review Chapter Results |  |  |  | 15m | NORMAL
VIII | 6. Creating an Authenticated Single Page Application (SPA) | Minh Le | 2021-02-19 | 2021-02-20 | 4h 45m | HIGH
| Create Single Page Application |  |  |  | 1h 30m | NORMAL
| Config AAA |  |  |  | 1h | HIGH
| AWS-XRay |  |  |  | 30m | NORMAL
| Challenge - Update CloudFormation Template |  |  |  | 1h 30m | HIGH
| Review Chapter Results |  |  |  | 15m | NORMAL
IX | 7. Create Immersive Experiences with Amazon AI Services | Minh Le | 2021-02-21 | 2021-02-22 | 5h 15m | HIGH
| Adding Speech with Amazon Polly |  |  |  | 1h | HIGH
| Object Recognition with Rekognition |  |  |  | 1h 30m | HIGH
| Chatbot with Lex |  |  |  | 1h 30m | HIGH
| Challenge |  |  |  | 1h | NORMAL
| Review Chapter Results |  |  |  | 15m | NORMAL

## Timeline
Renova DevAx M2M - Timeline